Measuring Results of the Functional Literacy Activity of the Artisan and Fez Medina Project

# In Context

The MCC compact with Morocco was a five-year investment (2008-2013) of $666.4 million in five projects:  Fruit Tree Productivity; Small Scale Fisheries; Artisan and Fez Medina, which included the Functional Literacy and Vocational Training (FLVT) activity; Financial Services; and Enterprise Support.

This $84 million Artisan and Fez Medina Project represented 13% of the total compact and aimed to stimulate economic growth by leveraging the links between the craft sector, tourism, and the Fez Medina’s rich cultural, historic and architectural assets. The Artisan and Fez Medina project consisted of the Artisan Component that included the Artisan Production and Promotion Activities, the Fez Medina Activity, and the Functional Literacy and Vocational Training Activity.

This performance evaluation focusses on the $31.7 million Functional Literacy and Vocational Training (FLVT) Activity which represented 5% of the total compact, and sought to:

- Provide basic literacy skills – these skills included reading, writing, and arithmetic and these skills’ applications to major functions and tasks in all three sectors (agriculture, handicraft, and artisan fisheries)

- Enhance vocational skills of men, women, and young people – the strengthening of vocational skills within the three sectors (agriculture, handicraft, fisheries) especially reinforced workers’ independence in their respective enterprises.

- Develop transferable skills and life skills – this would improve the autonomy of the beneficiaries through promoting awareness of civic rights, improving the capacity of managing work activities, professional organization, and how to start income generating projects.

To do this, the project financed the training of literacy teachers and supervisors to develop their skills in new media, life-long learning approaches, and the process of monitoring, evaluation, and plan management.

The FLVT also set up a certification program to assess and validate the skills of the beneficiaries, to motivate them, to provide recognition of their skills for the job market, and to give them the opportunity to access further training and more advanced vocational qualification programs.

# Program Logic

The functional literacy activity aimed to contribute to the improvement in productivity, employability, and income of 30,000 artisans, 20,000 fishers, and 19,000 farmers, through upgrading their basic education and professional qualifications.

The targeted population is composed of 69,000 beneficiaries of the Fruit Tree Productivity, Small Scale Fisheries, and Artisan Production projects, as well as their families.

| Inputs | Outputs | Outcomes | Impact |
| --- | --- | --- | --- |
| MCC investments helped: - To recruit an activity manager; - To establish an agreement with UNESCO to develop functional literacy curricula and certification examination for each of the three sectors of agriculture, handicrafts, and artisan fisheries; - To engage government entities (MAPM, MA), NGOs, literacy facilitators, supervisors and managers to provide literacy programming; - To provide teaching/learning equipment to classrooms; - To train certifiers and administer certification exams. | - Functional literacy standards, curricula, and learning materials are developed for the three sectors - A two-level functional literacy certification examination system is developed and implemented - The farmers, artisans, and fishermen are certified as literate; - The capacity of literacy facilitators, supervisors and managers is strengthened; - The literacy classrooms are equipped; | - Improved productivity of artisans, farmers and fishers; - Better access to job opportunities and income generating activities; - Technological innovations are adopted in terms of production and adaptation to market demand; - Certification program institutionalized by stakeholders | - Beneficiaries’ revenue in the targeted sectors increased - Improved livelihoods and reduced of poverty in targeted areas |

There were several key assumptions underlying the Functional literacy activity logic during the design of the investment:

- Illiteracy is a major constraint for the growth of the sectors targeted by the Compact: Agriculture, handicraft and artisan fisheries. Literate artisans, farmers and fishers would be more open to innovations and would be keen to adopt the techniques and organizations recommended by the three projects.

- A functional literacy activity based on learning to read, write and count, among other professional and life skills, would open new employment and professional opportunities. Due to the acquired skills and the increased likelihood of adopting modern techniques, the employability and the productivity of beneficiaries would rise.

- Farmers, artisans and artisan fishers are aware of the illiteracy constraint weighing on their productivity and employability and would be motivated to benefit from the project.

- The Ministry of Agriculture and Fisheries and the Ministry of Artisans would designate further training opportunities and education qualifications for which the literacy certification serves as a perquisite.

Measuring Results

MCC uses multiple sources to measure results. Monitoring data is used during compact implementation.  Independent evaluations are generally completed post compact. Monitoring data is typically generated by the program implementers, and specifically covers the program participants who received treatment through the compact. MCC conducts performance evaluations to assess whether the program was adequately designed to meet the needs of the program beneficiaries and how the program was implemented. This particular performance evaluation used the following criteria to assess the program activities: coherence, efficiency, effectiveness, applicability, and durability.

Monitoring Results

The following table summarizes the performance of output and outcome indicators specific to the evaluated program.

| Indicators | Level | Target | Actual | % Female | Completion rate |
| --- | --- | --- | --- | --- | --- |
| Students participating in the MCC-supported functional literacy program | Output | 69,000 | 69,731 | 67% | 101% |
| Graduates of MCC-supported Functional Literacy program (passed certification) | Outcome | 41,491 | 38,708 | 81% | 93% |
| Instructors trained for Functional Literacy | Output | 2,400 | 1,856 | 95% | 77% |
| Number of class rooms equipped for literacy training | Output | 130 | 130 | - | 100% |

The average completion rate of outcome, output, and process indicators’ targets is 93 percent; and for 3 out of the 4 indicators, targets are met at 93% or above.

## Evaluation Questions

The principal questions targeted by the evaluation were:

- To what extent have the expected results for the Functional Literacy sub-activity been achieved, in particular, in terms of the number of certified?

- To what extent did the results effectively contribute to the achievement of the final goal of the activity, and/or they could contribute in the future;

- Have the beneficiaries adopted the recommended techniques in terms of life skills and professional skills?

- What are the constraints and the measures put in place to ensure the participation of women and girls in the activity?

## Evaluation Results

The impact of the project on the beneficiaries was generally positive, observed mainly by the 82% of enrollees in all three sectors who had learned to read, write, do arithmetic, and perform other life skills.  The project met 93% of its goal of getting 80% of enrolled learners certified.   82% of men and 91% of women who were certified, said certification is important for career advancement.

The high representation of females in the training sessions and among literacy facilitators and managers confirmed the relevance of the community-based and flexible hours approach adopted to the objective of improving women and girls’ skills.  Women, whom were highly represented among certified learners, said they saw certification as bringing them important recognition in the eyes of their families and children.

The value-added from implementing a functional literacy approach appeared promising in terms of improving sources of income for beneficiaries, particularly the creation of income-generating projects and the use of new technologies to improve performance. For instance, 74.6% of beneficiaries stated that they use the new technologies daily in the course of their professional activities. From information gathered from beneficiaries in focus groups or semi-structured interviews, the evaluator expected productivity gains of 20%, 40% or even 60% over time, but this was highly dependent on various exogenous factors noted by farmers, fishers and artisans (e.g. better product marketing conditions, price fluctuations, and ability to access new technologies to innovate).

Although it was difficult to measure the ultimate impact of the Functional Literacy Activity on the incomes and living standards of beneficiaries, the study of 500 beneficiaries found that 66.8% of them anticipated that they would improve their incomes due to the training they received. Similarly, the program positively impacted the degree of optimism and willingness to believe in the change that functional literacy fostered in the beneficiaries.

Beyond the impact on the beneficiaries and their families, the program inspired the National Agency for Combatting Illiteracy, the new agency created to promote literacy in Morocco, with the teaching tools used, and the management and monitoring approach, and will consolidate and sustain the program in future operations. The nearly 2000 highly trained literacy facilitators would contribute to achieve the goals of this agency.  The certification process (tests, guides, procedures) was also officially adopted by the Government of Morocco, but may require additional adaptation for different training programs.

Evaluation results of the activity are summarized in the table below:

| Evaluator | Consortium: Transtec/Attitude Conseil |
| --- | --- |
| Methodology | A performance evaluation based on pre-post approach, which included a survey of a sample of 500 beneficiaries, 17 focus groups (of which there were 3 types: beneficiaries, literacy workers, and functional literacy service providers), and 70 semi-structured interviews with all categories of stakeholders |
| Evaluation Period | April 2013 to November 2013 |
| Immediate Outcomes | Outputs - 82.4% of beneficiaries indicated they had learned to read, write, and do arithmetic by the end of the cycle - 40.2% of beneficiaries said they had learned about their civil and worker’s rights and responsibilities Relevance - 70% of beneficiaries had their needs met by the program - 96% were satisfied with the literacy workers’ skills and facilitation techniques - 70% of beneficiaries considered the new techniques acquired from the FL activity as adapted and easy to use Sustainability - 74.6% of beneficiaries stated that they use the new technologies daily in the course of their professional activities |
| Intermediate Outcome | It is too early to assess the employability and the productivity improvement due to the project, but: - Different scenarios estimate future productivity gains at 20%, 40%, or even 60% over time (although this is highly dependent on various exogenous factors experienced by farmers, fishers and artisans) |
| Ultimate Impact | It is too early to assess the impact on incomes and standards of living, but: - 66.8% of beneficiaries anticipated that their incomes would improve as a result of the trainings - There was a positive trend in the degree of optimism and willingness to believe in the change that functional literacy fostered in the beneficiaries |

## Lessons Learned

The main lessons from this activity are:

- Stronger integration between projects and activities: The intervention logic of the MCA Compact, which enlisted the functional literacy sub-activity as an integrated action and support for the different income-generating projects, largely responds to the global objective to fight poverty.  However, implementation of the sub-activity after it was adjusted was not sufficiently harmonized with the sectorial projects planned in the MCA. The enrollees in the functional literacy cycles were often not the people or families benefiting from other sectorial projects of the program, which limits the direct results that can be expected from the functional literacy sub-activity in terms of combatting poverty. Support what is acquired through the PAF in order to improve the sources of income of beneficiaries, particularly the creation of projects and the use of new technologies, and encourage this dynamic through appropriate support within the framework of national sectorial plans.

- Specialization of literacy approach: A workplace-based/sector-based literacy approach can benefit from more involvement of professionals from that sector, to facilitate skills for employability and productivity. Additionally, expanding the functional literacy approach to other sectors, particularly health, tourism, social action, and industry, would open up the possibility for other sectorial development programs that can better mobilize human resources.

- Focus on sustainability: The program targeted substantial changes (behaviors, independence) that take time, so it is necessary to strengthen results through actions directed at sustainability, immediate assistance and economic support of beneficiaries to ensure their newly acquired skills are not lost.

- Organizational leadership: The newly created National Agency to Combat Illiteracy (ANLCA) should exert a leadership to achieve significant progress in strengthening the convergence in program content, management and monitoring/evaluation of functional literacy programs carried out by different operators: public sector, private sector, NGOs, domestic and international donors (this also includes harmonizing compensation for trainers and service providers, and subsidies for NGOs).

- Institutionalization of bridging mechanisms: In view of the importance attributed by the beneficiaries to certification in terms of improving their professional and social situation, and by trainers and service providers in demonstrating the value of their efforts, the Government should assess ways to institutionalize bridging mechanisms between literacy and vocational attainment so that literacy graduates could access more vocational training opportunities (Only Fisheries had bridging opportunities).