El Salvador

MCC Learning from

“Evaluation of the Formal Technical Education Sub-Activity of the Human Development Project, El Salvador”

Mathematica Policy Research, June 2016

MCC has identified the following programmatic and evaluation lessons based on the “Evaluation of the Formal Technical Education Sub-Activity of the Human Development Project, El Salvador.”

PROGRAMMATIC LESSONS

- In order to be sustainable, projects should integrate new activities into the already existing system and improve the system where necessary. Teacher training took place by consultants paid with compact funds during implementation, but the on-going teacher training program was ad hoc and teachers and students viewed it be insufficient. This means that new teachers receive informal training from fellow teachers, which puts the reputation of the MEGATEC degrees at risk. It’s important to analyze whether or not a one-off training of teachers represents the highest return or if a systematic improvement to teacher training would provide higher returns. Additionally, the management of the consultants was conducted largely without the Ministry of Education. This can limit ownership and the potential for increasing Ministry capacity. However, the Ministry would have needed additional human resources to do this effectively.

- Involvement of the private sector is an important aspect of providing quality education and training. Results from the ITCHA evaluation suggest that there may not be enough local labor market demand to absorb secondary school and ITCHA graduates, particularly graduates with alternative tourism degrees. Additionally, the ITCHA had difficulties finding adequate internships for their students. This highlights the importance of having a mechanism to ensure the provision of training is closely linked to the skills demanded in the local or regional labor market.

- Sustainability mechanisms need to be incorporated into project design from the beginning. Even though many of the components of the sub-activity have been found to have short-term impacts, there is concern about the sustainability of some of the investments, and therefore the sustainability of impacts on outcomes. For example, the funding for scholarships for both secondary schools and ITCHA ended with the compact and it is now the responsibility of the Ministry of Education (MINED) to continue providing them or find another provider. Without continuation of the scholarship program, transportation and other indirect costs will remain significant barriers to student

enrollment, particularly for boys. Another example is that while the project succeeded in bringing in new types of teachers with relevant practical experience – after the project, in some cases, they were replaced by more traditional teachers. Demonstrating a new model or approach through exceptions to rules can be a viable short term strategy, but they should be linked to longer term reform efforts to build on the demonstration effect.

EVALUATION LESSONS

- Project design determines what can be evaluated. An evaluation cannot establish the differential impact of individual components of a package of interventions unless the project is designed to test different components. To do so, different pieces of the package would have to be provided to different groups of beneficiaries. If a package is provided in its entirety, the package will be evaluated and the evaluator will not be able to disentangle the impacts of individual components. This has been illustrated through the evaluation of the Technical Secondary School Strengthening. The evaluation cannot tell us if the increased enrollment is coming from improved infrastructure, better trained teachers, new curriculum, or scholarships. If, for example, scholarships had been made available to a sub-set of students in the comparison schools, the evaluation would have been able to more easily tease out the impact of the school strengthening from the impact of the scholarship. However, the desire and ability to perform such an evaluation depends on the program logic, budget, and the complexity of implementation.

- Random assignment can be a fair and transparent mechanism to distribute finite resources and allow for a rigorous impact evaluation. In El Salvador, random assignment was seen as a fair way to distribute scholarships when qualified demand exceeded supply. Scholarships were offered for multiple years and the random selection was only conducted in the year where there were more qualified applicants who met the minimum criteria than scholarships available. By randomly selecting scholarship recipients, the applicants who were not offered scholarships were similar to those offered scholarships and thus created a strong control group to measure impact. The random assignment method (a computerized lottery conducted publicly) was transparent and it was clear that each eligible applicant had an equal chance to receive the scholarship.

- Projects and evaluations should invest in improving the quality and availability of administrative data. Initially, the plan was that much of the data used for these evaluations would come from administrative records from MINED. However, within MINED, school-level and student-level data come from two different departments and they are not consistent with each other. The two data sources use different definitions for counting enrollment, drop-outs from one school are not tracked to see if they enroll in a different school, and some records have been found incomplete. For this final evaluation, MCC used a third party data collector to gather data directly from schools. MCC did not design the project or the evaluation to invest in improving data quality or availability and therefore, the MINED data has significant weaknesses which limit the quality of decisions that can be made based on those data. The quality of data and the use of data within MINED could be improved to help manage El Salvador’s education sector and improve the accuracy of evaluation analyses.